## Instructions
Project Planner & Gantt Chart
FREE LITE VERSION · by CalcHub Templates · see the “Upgrade to Full” tab for the complete Project Planner & Gantt Chart
HOW TO USE:
1. Settings: project name, manager, the date the Gantt timeline starts, planned finish date and budget. Edit the Phases and Team lists.
2. Gantt: one row per task — name, phase and owner (dropdowns), start date, duration in days, % done and cost. The end date, status and the coloured bars on the 26-week timeline draw themselves.
Blue = planned, green = done, red = late; the current week is highlighted. Use a 1-day task with ◆ in the name for milestones.
3. Risks & Issues: log risks with impact and likelihood (1–5). Scores of 12 or more turn red.
4. Dashboard: overall progress (weighted by duration), tasks done, late tasks, forecast finish, days left, cost vs budget, progress by phase, workload by owner and tasks due in the next 14 days.
TIPS:
• Update % done every Friday — it takes two minutes and keeps the dashboard honest.
• Status 'Should start' means the start date has passed but nothing is logged yet.
• Need a longer timeline? Move the Gantt start date forward on Settings.
EXAMPLE DATA:
The example (red banners) is a 4-month website redesign. Select the yellow example cells on Gantt and Risks, press Delete, and plan your own project.
COLOUR KEY:
Yellow cells = your inputs (type here)
Blue cells = formulas (calculated automatically — please don't type over them)
Red banner = example data. To start fresh: select the yellow example rows and press Delete (never delete whole rows/columns).
Works in Microsoft Excel (2010+), Google Sheets (File > Import > Upload) and LibreOffice. No macros.
Disclaimer: for educational planning only; not financial, tax or legal advice.

## Upgrade to Full
Upgrade to the full Project Planner & Gantt Chart
You are using the free lite version · CalcHub Templates · $9.99 one-time
▶ Buy the full version — $9.99 (instant download)
▶ Best value: all 30 products in the Everything Bundle — $18.99 (worth $179.50)
Secure checkout by Lemon Squeezy. Works in Excel, Google Sheets & LibreOffice.
Feature | Free lite | Full version
Tasks on the Gantt chart | 12 | 150
Automatic Gantt bars & late alerts | ✓ | ✓
Progress by phase & owner | ✓ | ✓
Risks & issues log | — | ✓
Charts | — | ✓
Quick-start PDF guide | — | ✓
The full version also includes:
✓ Automatic Gantt bars
✓ Late-task & due-soon alerts
✓ Phase progress & owner workload
Full product description
Type tasks with a start date and duration and the 26-week Gantt chart draws itself, with late tasks in red, progress by phase, workload by owner, cost vs budget and a risk log.
Free lite version — personal use. Please share the download page rather than the file.

## Settings
Project Settings (Free Lite)
Name, dates, team and phases
EXAMPLE DATA — replace the yellow cells with your own numbers
Project name | Website Redesign
Project manager | Alex Kim
Gantt start date | 2026-08-24
Planned finish date | 2026-12-18
Budget | 48000
|  | PHASES | TEAM
|  | Discovery | Alex
|  | Design | Sam
|  | Build | Priya
|  | Test | Jo
|  | Launch | Mia
Vendor

## Dashboard
Project Dashboard (Free Lite)
Progress, deadlines and workload at a glance
OVERALL PROGRESS |  | TASKS DONE |  | LATE TASKS | FORECAST FINISH |  | DAYS LEFT |  | COST PLANNED vs BUDGET
BY PHASE |  |  |  |  | BY OWNER
Phase | Tasks | Done | Progress | Cost | Owner | Open tasks | Late | Days of work
STATUS |  |  | DUE IN THE NEXT 14 DAYS
Status | Tasks
Done
In progress
Should start
Late
Not started

## Gantt
Gantt (Free Lite)
Tasks on the left, timeline on the right · bars draw themselves
EXAMPLE DATA — select the yellow example rows, press Delete, then enter your own
# | Task | Phase | Owner | Start | Days | End | % done | Status | Cost | Done days
| Kick-off & goals | Discovery | Alex | 2026-08-24 | 3 |  | 100% |  | 800
| Stakeholder interviews | Discovery | Priya | 2026-08-27 | 8 |  | 100% |  | 2400
| Analytics & content audit | Discovery | Jo | 2026-08-31 | 7 |  | 100% |  | 1800
| Sitemap & user flows | Design | Priya | 2026-09-08 | 8 |  | 100% |  | 2600
| Wireframes | Design | Priya | 2026-09-16 | 12 |  | 90% |  | 4200
| Visual design | Design | Sam | 2026-09-28 | 15 |  | 80% |  | 6800
| Design sign-off ◆ | Design | Alex | 2026-10-14 | 1 |  | 0% |  | 0
| Front-end build | Build | Jo | 2026-10-12 | 25 |  | 20% |  | 12000
| CMS setup & content | Build | Mia | 2026-10-20 | 20 |  | 15% |  | 5200
| Integrations | Build | Vendor | 2026-10-26 | 14 |  | 0% |  | 4800
| QA & accessibility | Test | Jo | 2026-11-23 | 10 |  | 0% |  | 3000
| User testing | Test | Priya | 2026-11-30 | 7 |  | 0% |  | 1800
🔒 Free lite version: 12 rows. Unlock more rows, charts and all features in the full version — see the "Upgrade to Full" tab.